**Sprint Planning**

**Sprint planning-01**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sprint No** | **Total Feature** | | **Start Date** | | **End Date** | | **Total Days** | **Total Estimate hour** | |
| **01** | **2** | | **25/09/2020** | | **30/09/2020** | | **6** | 79 | |
| **Product backlog** | **Story point** | **Spilt Task** | | | **Assigned to** | **Start time** | **End Time** | **Estimate hour** | **Status** |
| Required technology installation and setup project | 5 | SharePoint installation | | | Developer | 25/09/2020 | 25/09/2020 | 5 | Done |
| Take a feed back and plan next Task | | | Scrum master | 26/09/2020 | 26/09/2020 | 2 | Done |
|  | | | | | | | | | |
| Students need to see the all course offers of university in this system and get admission related information. | 13 | Analysis to the university all type of course offers and admission system | | Analyst | | 26/09/2020 | 28/09/2020 | 15 | Done |
| Course offers page UI design | | Designer | | 26/09/2020 | 28/09/2020 | 18 | Done |
| Create and add course offer and admission process | | Developer | | 27/09/2020 | 30/09/2020 | 28 | Done |
| Testing the Course offers and admission process how properly work in this system | | Tester | | 29/09/2020 | 30/09/2020 | 8 | Done |
| Take a feedback for this product | | Scrum master | | 29/09/2020 | 30/09/2020 | 8 | Done |

Sprint planning-02

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sprint No** | **Total feature** | | **Start Date** | **End Date** | | **Total Days** | **Total Estimate hour** | |
| **02** | **O1** | | **01/10/2020** | **06/10/2020** | | **6** | **83** | |
| **Feature** | **Story point** | **Spilt Task** | | **Assigned to** | **Start time** | **End Time** | **Estimate hour** | **Status** |
| Student or visitor can do the any quires direct for university authority through the enquiry form. | 13 | Analysis how the student or visitor enquiry type in this system | | Analyst | 01/10/2020 | 03/10/2020 | 15 | Done |
| Design enquiry UI page | | Designer | 01/10/2020 | 03/10/2020 | 15 | Done |
| Create and develop this enquiry system and this enquiry must be implement database | | Developer | 02/10/2020 | 06/10/2020 | 35 | Done |
| Testing the enquiry system | | Tester | 05/10/2020 | 06/10/2020 | 10 | Done |
| Take the feedback every day full sprint for this product | | Scrum Master | 02/10/2020 | 06/10/2020 | 8 | Done |

Sprint planning-03

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sprint No** | **Total feature** | | **Start Date** | **End Date** | | **Total Days** | **Total Estimate hour** | |
| **03** | **02** | | **07/10/2020** | **13/10/2020** | | **6** | **94** | |
| **Feature** | **Story point** | **Spilt Task** | | **Assigned to** | **Start time** | **End Time** | **Estimate hour** | **Status** |
| Student's visitors will be able to see all the campus contact information of the university | 5 | Analysis the contact information and how possible output database in this contact page | | Analyst | 07/10/202 | 08/10/2020 | 10 | Done |
| Design contact UI page | | Designer | 07/10/2020 | 08/10/2020 | 8 | Done |
| Create contact page and add contact information and implement backend database | | Developer | 08/10/2020 | 11/10/2020 | 20 | Done |
| Testing the contact page how this page show the information | | Tester | 10/10/2020 | 11/10/2020 | 6 | Done |
| Take the feedback for this feature and plan to next feature | | Scrum Master | 10/10/2020 | 11/10/2020 | 4 | Done |
|  | | | | | | | | |
| Visitor or student all time can see the university current news | 8 | Analysis the university news type information | | Analyst | 09/10/2020 | 10/10/2020 | 8 | Done |
| Design news related page for this system | | Designer | 09/10/2020 | 10/10/2020 | 10 | Done |
| Create news section page and add news type for this system | | Developer | 11/10/2020 | 13/10/2020 | 18 | Done |
| Testing how news page to show and work properly in this system | | Tester | 12/10/2020 | 13/10/2020 | 4 | Done |
| Take the feedback for this product items | | Scrum Master | 12/10/2020 | 13/10/20 | 6 | Done |

Sprint planning- 04

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sprint No** | **Total feature** | | **Start Date** | **End Date** | | **Total Days** | **Total Estimate hour** | |
| **04** | **02** | | **15/10/2020** | **21/10/2020** | | **6** | **114** | |
| **Feature** | **Story point** | **Spilt Task** | | **Assigned to** | **Start time** | **End Time** | **Estimate hour** | **Status** |
| Visitor or student can see the previous student success stories in this alumni forum. | 8 | Analysis the how to involve alumni information and previous student success story information in this system | | Analyst | 15/10/2020 | 16/10/2020 | 12 | Done |
| Design the alumni and previous student success story page UI | | Designer | 15/10/2020 | 16/10/2020 | 14 | Done |
| Create and add the alumni and previous student success story page in for this system | | Developer | 16/10/2020 | 19/10/2020 | 20 | Done |
| Testing the alumni and previous page properly work in this section | | Tester | 18/10/2020 | 19/10/2020 | 8 | Done |
| Take the feedback for this product | | Scrum Master | 18/10/2020 | 19/10/2020 | 6 | Done |
|  | | | | | | | | |
| Student or visitor can see the university research publication information through this system. | 8 | Analysis the university system how include their research work and student or visitor see the research information | | Analyst | 17/10/2020 | 18/10/2020 | 10 | Done |
| Design research page UI | | Designer | 17/10/2020 | 19/10/2020 | 12 | Done |
| Create and add the research page and information in this system | | Developer | 19/10/2020 | 21/10/2020 | 18 | Done |
| Testing the research page | | Tester | 20/10/2020 | 21/10/2020 | 6 | Done |
| Take the feedback for this sprint and plant to next sprint this product items | | Scrum Master | 19/10/2020 | 21/10/2020 | 8 | Done |

Sprint planning-05

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sprint No** | **Total feature** | | **Start Date** | **End Date** | | **Total Days** | **Total Estimate hour** | |
| **05** | **01** | | **24/10/202** | **27/10/202** | | **6** | **46** | |
| **Feature** | **Story point** | **Spilt Task** | | **Assigned to** | **Start time** | **End Time** | **Estimate hour** | **Status** |
| This system include the university about information | 5 | Analysis this page how possible output for this system | | Analyst | 24/10/2020 | 25/10/2020 | 10 | Done |
| Design about page UI for this system | | Designer | 24/10/2020 | 25/10/2020 | 12 | Done |
| Create about page and add about information in this system | | Developer | 25/10/2020 | 27/10/2020 | 15 | Done |
| Test this about information | | Tester | 26/10/2020 | 27/10/2020 | 4 | Done |
| Take the feedback for this product | | Scrum Master | 25/10/2020 | 27/10/2020 | 5 | Done |
|  | | | | | | | | |